## Submittal Log Template
Submittal Log Sample Template |  |  |  | Submittal Review Flow
Division | Submittal # | Section Title & Description | Long Lead Time - Comments | AHJ Required Review | SRM Construction (PE) | SRM Construction (Supt) | Owner's Rep | Civil Engineer | Strutural Engineer | Building Envelope Consultant | Facade Access Consultant | Mechanical Engineer | Plumbing Engineer | Electrical Engineer | Lighting Consultant | Food Service Designer | Interior Designer | Acoustical Consultant | Landscape Architect | Architect
Div 02 |  | Existing Conditions/Demolition
| 2.1 | Remediation & Abatement
| 2.1.01 | Hazardous Material Assessment |  | X | X | X | X
| 2.1.02 | Dispoal Manifests |  | X | X | X | X
| 2.2 | Selective Demolition
| 2.2.01 | Demolition plan |  | X |  | X
| 2.2.02 | OSHA project permit |  | X | X | X
| 2.2.03 | Disposal Manifests |  | X | X | X
Div 03 |  | Concrete
| 3.1 | Structural Concrete
| 3.1.01 | Concrete Mix Designs |  | X | X | X |  |  | X | [10 empty] | X
| 3.1.02 | Shotcrete Mix Designs |  | X | X | X |  |  | X | [10 empty] | X
| 3.1.03 | Shotcrete Test Panel |  |  | X | X |  |  | X | [10 empty] | X
| 3.1.04 | Concrete Curing Compounds |  |  | X |  |  |  | X | [10 empty] | X
| 3.1.05 | Vapor Barrier |  |  | X |  |  |  | X | X | [9 empty] | X
| 3.1.06 | Waterstop at Cold Joints |  |  | X |  |  |  | X | X | [9 empty] | X
| 3.1.07 | Rebar Shop Drawings - Footings |  |  | X | X |  |  | X | [10 empty] | X
| 3.1.08 | Rebar Shop Drawings - Columns |  |  | X | X |  |  | X | [10 empty] | X
| 3.1.09 | Rebar Shop Drawings - SOG |  |  | X | X |  |  | X | [10 empty] | X
| 3.1.10 | Rebar Shop Drawings - PT Deck |  |  | X | X |  |  | X | [10 empty] | X
| 3.1.11 | Studrail Shop Drawings - PT Deck |  |  | X | X |  |  | X | [10 empty] | X
| 3.1.12 | PT Cable Shop Drawings |  |  | X | X |  |  | X | [10 empty] | X
| 3.1.13 | Shoring/Reshore Engineered Shop Drawings |  |  | X | X |  |  | X | [10 empty] | X
| 3.1.14 | Structural Foam - Topping Slabs |  |  | X | X |  |  | X | [10 empty] | X
| 3.1.15 | Embedded Hardware Shops & Product Data |  |  | X | X |  |  | X | [10 empty] | X
| 3.2 | Gypcrete
| 3.2.01 | Gypcrete - Product Data |  |  | X | [12 empty] | X |  | X
| 3.2.02 | Acoustima - Product Data |  |  | X | [12 empty] | X |  | X
| 3.2.03 | Gypcrete Primer - Product Data |  |  | X | [12 empty] | X |  | X
| 3.2.04 | Perimeter Isolator Foam - Product Data |  |  | X | [12 empty] | X |  | X
| 3.3 | Hardrock Concrete Topping
| 3.3.01 | Concrete Mix Designs |  |  | X | X |  |  | X | [10 empty] | X
| 3.3.02 | Concrete Data Sheets |  |  | X |  |  |  | X | [10 empty] | X
Div 04 |  | Masonry
| 4.1 | Unit Masonry - CMU
| 4.1.01 | Concrete Masonry Unit - Product Data |  |  | X |  |  |  | X | [10 empty] | X
| 4.1.02 | Grout - Product Data |  |  | X |  |  |  | X | [10 empty] | X
| 4.1.03 | Mix Design - Footings |  |  | X |  |  |  | X | [10 empty] | X
| 4.2 | Brick Masonry
| 4.2.01 | Brick Masonry - Product Data |  |  | X | [14 empty] | X
| 4.2.02 | Masonry Ties & Anchors |  | X | X | [14 empty] | X
| 4.2.03 | Grout - Product Data |  |  | X | [14 empty] | X
| 4.2.04 | Grout - Color Samples |  |  | X | X | [13 empty] | X
| 4.2.05 | Masonry Grade SAM (Self-Adhered Membrane) |  |  | X |  |  |  |  | X | [9 empty] | X
| 4.2.06 | Sealer |  |  | X |  | X | [12 empty] | X
| 4.3 | Stone/Brick Veneer
| 4.3.01 | Veneer - Product Data |  |  | X | X | [13 empty] | X
| 4.3.02 | Masonry Ties & Anchors |  |  | X | X | [13 empty] | X
| 4.3.03 | Grout - Product Data |  |  | X | X | [13 empty] | X
| 4.3.04 | Grout - Color Samples |  |  | X | X | [13 empty] | X
| 4.3.05 | Sealer |  |  | X |  | X |  |  | X | [9 empty] | X
| 4.4 | Precast
| 4.4.01 | Precast Shop Drawings |  |  | X | X | [13 empty] | X
| 4.4.02 | Precast - Product Data |  |  | X | [14 empty] | X
| 4.4.03 | Precast Ties & Anchors |  | X | X | X | [13 empty] | X
| 4.4.04 | Grout - Product Data |  |  | X | [14 empty] | X
| 4.4.05 | Grout - Color Samples |  |  | X | X | [13 empty] | X
Div 05 |  | Metals
| 5.1 | Structural Steel
| 5.1.01 | Embed Shop Drawings & Layout |  |  | X | X |  |  | X | [10 empty] | X
| 5.1.02 | HSS Column Templates |  |  | X | X |  |  | X | [10 empty] | X
| 5.1.03 | Steel Column, Beam and Framing Shops |  |  | X | X |  |  | X | [10 empty] | X
| 5.1.04 | Misc Lintel Shop Drawings |  |  | X | X |  |  | X | [10 empty] | X
| 5.1.05 | Canopy Steel Shop Drawings |  | X | X | X |  |  | X | [10 empty] | X
| 5.1.06 | Metal Stair Shop Drawings & Calculations |  | X | X | X |  |  | X | [10 empty] | X
| 5.1.07 | Field Welding Procedures |  |  | X |  |  |  | X | [10 empty] | X
| 5.2 | Decklets & Railings
| 5.2.01 | Bolt-On Deck Shop Drawings & Calculations |  | X | X | X |  |  | X | [10 empty] | X
| 5.2.02 | Balcony Railing Shop Drawings & Calculations |  | X | X | X |  |  | X | [10 empty] | X
| 5.2.03 | Guardrail Shop Drawings & Calculations |  | X | X | X |  |  | X | [10 empty] | X
| 5.2.04 | Handrail Shop Drawings |  |  | X | X |  |  | X | [10 empty] | X
| 5.2.05 | Finish Selection - Product Data |  |  | X | [14 empty] | X
| 5.2.06 | Color Samples |  |  | X | [14 empty] | X
| 5.3 | Cold Formed Metal Framing
| 5.3.01 | Cold Formed Metal Framing - Product Data |  |  | X |  |  |  | X | [10 empty] | X
| 5.3.02 | Hold-Down Shop Drawings |  | X | X | X |  |  | X | [10 empty] | X
| 5.3.03 | Hold-Down and Fastener - Product Data |  |  | X |  |  |  | X | [10 empty] | X
| 5.3.04 | Shearwall - Concrete Anchors |  |  | X | X |  |  | X | [10 empty] | X
| 5.3.05 | Level 1 Wall Shop Drawings |  |  | X | X |  |  | X | [10 empty] | X
| 5.3.06 | Level 2 Wall Shop Drawings |  |  | X | X |  |  | X | [10 empty] | X
| 5.3.07 | Level 3 Wall Shop Drawings |  |  | X | X |  |  | X | [10 empty] | X
| 5.3.08 | Level 2 Floor Shop Drawings |  |  | X | X |  |  | X | [10 empty] | X
| 5.3.09 | Level 3 Floor Shop Drawings |  |  | X | X |  |  | X | [10 empty] | X
| 5.3.10 | Roof Panel/Joist Shop Drawings |  | X | X | X |  |  | X | [10 empty] | X
| 5.3.11 | Roof Truss Shop Drawings |  | X | X | X |  |  | X | [10 empty] | X
Div 06 |  | Rough Carpentry
| 6.1 | Wood Framing
| 6.1.01 | Engineered Lumber - Product Data |  |  | X |  |  |  | X | [10 empty] | X
| 6.1.02 | Joist/TJI Shop Drawings |  | X | X | X |  |  | X | [10 empty] | X
| 6.1.03 | Roof Truss Shop Drawings |  | X | X | X |  |  | X | [10 empty] | X
| 6.1.04 | Hold-Down Shop Drawings & Layout |  | X | X | X |  |  | X | [10 empty] | X
| 6.1.05 | Hold-Down - Product Data |  |  | X |  |  |  | X | [10 empty] | X
| 6.1.06 | Fastners, Anchors & Adhesives - Product Data |  |  | X |  |  |  | X | [10 empty] | X
| 6.2 | Specialty Casework
| 6.2.01 | Common Area Casework Shop Drawings |  |  | X | X | [10 empty] | X |  |  | X
| 6.2.02 | Product Data Sheets |  |  | X | [11 empty] | X |  |  | X
| 6.2.03 | Backing Layout |  |  | X | X | [10 empty] | X |  |  | X
| 6.2.04 | Finish Selection Charts & Samples |  |  | X | [11 empty] | X |  |  | X
| 6.3 | Millwork
| 6.3.01 | Unit Millwork - Product Data |  |  | X |  | X | [9 empty] | X |  |  | X
| 6.3.02 | Common Area Millwork - Product Data |  |  | X |  | X | [9 empty] | X |  |  | X
Div 07 |  | Thermal & Moisture Protection
| 7.1 | Below Grade Waterproofing
| 7.1.01 | Bentonite/Fluid Applied Below Grade WP - Product Data |  |  | X | X |  |  |  | X | [9 empty] | X
| 7.1.02 | Drain Mat and Total Drain Collection System |  |  | X | X |  |  |  | X | [9 empty] | X
| 7.1.03 | Penetration Waterproofing Detailing |  |  | X | X |  |  |  | X | [9 empty] | X
| 7.1.04 | Termination Bar & Sealant - Product Data |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.2 | Horizontal Waterproofing
| 7.2.01 | Hot Rubber or Cold Fluid Applied - Product Data |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.2.02 | Drain Mat & Protection Board - Product Data |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.2.03 | Penetration Waterproofing Detailing |  |  | X | X |  |  |  | X | [9 empty] | X
| 7.2.04 | Alsan/PMMA - Product Data |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.2.05 | Water Test Requirements |  |  | X | X |  |  |  | X | [9 empty] | X
| 7.3 | Pedestrian Traffic Coatings
| 7.3.01 | Traffic Coating - Product Data |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.3.02 | Finish Selection - Color Chart |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.3.03 | Penetration Waterproofing Detailing |  |  | X | Supt Req |  |  |  | X | [9 empty] | X
| 7.4 | Insulation
| 7.4.01 | Batt Insulation - Product Data |  |  | X |  |  |  |  | X | [7 empty] | X |  | X
| 7.4.02 | Mineral Wool - Product Data |  |  | X |  |  |  |  | X | [7 empty] | X |  | X
| 7.4.03 | Rigid Insulation - Product Data |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.4.04 | Spray Foam - Product Data |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.4.05 | Air Barrier Foam/Sealant - Product Data |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.5 | Membrane Built-Up Roofing
| 7.5.01 | Roof Membrane System - Product Data |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.5.02 | Self Adhered Vapor Barrier - Product Data |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.5.03 | Mechanical Fasteners and/or Adhesives |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.5.04 | Rigid & Tapered Insulation - Product Data |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.5.05 | Tapered Insulation Shop Drawings |  |  | X | X |  |  |  | X | [9 empty] | X
| 7.5.06 | Penetration Flashings |  |  | X | X |  |  |  | X | [9 empty] | X
| 7.5.07 | Term Bar & Sealants |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.5.08 | Walk Pads Layout |  |  | X | X |  |  |  | X | [9 empty] | X
| 7.6 | Tile Roofing
| 7.6.01 | Metal/Clay Tile Roofing System - Product Data |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.6.02 | Self Adhered Underlayment |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.6.03 | Battens |  |  | X | X |  |  |  | X | [9 empty] | X
| 7.6.04 | Roof Vent - Product Data & Layout |  |  | X | X |  |  |  | X | [9 empty] | X
| 7.6.05 | Roof Metals (Valley Gutters, Drip Edge, Bird Screen) |  |  | X | X |  |  |  | X | [9 empty] | X
| 7.6.06 | Penetration Flashings |  |  | X | X |  |  |  | X | [9 empty] | X
| 7.6.07 | Color Selection & Samples |  |  | X | [14 empty] | X
| 7.7 | Standing Seam Metal Roofing
| 7.7.01 | Standing Seam Metal Roofing System - Product Data |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.7.02 | Self Adhered Underlayment |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.7.03 | Roof Vent - Product Data & Layout |  |  | X | X |  |  |  | X | [9 empty] | X
| 7.7.04 | Roof Metals (Valley Gutters, Drip Edge, Bird Screen) |  |  | X | X |  |  |  | X | [9 empty] | X
| 7.7.05 | Penetration Flashings |  |  | X | X |  |  |  | X | [9 empty] | X
| 7.7.06 | Color Selection & Samples |  |  | X | [14 empty] | X
| 7.8 | Gutter & Downspouts
| 7.8.01 | Gutter & Downspout - Product Data |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.8.02 | Gutter & Downspout - Shop Drawings |  |  | X | X |  |  |  | X | [9 empty] | X
| 7.8.03 | Color Selection & Samples |  |  | X | [14 empty] | X
| 7.9 | Sheet Metal Flashings
| 7.9.01 | Sheet Metal Flashings - Product Data |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.9.02 | Sheet Metal Flashings - Shop Drawings |  |  | X | X |  |  |  | X | [9 empty] | X
| 7.9.03 | Self Adhered Membrane |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.9.04 | Sealants |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.9.05 | Color Selection & Samples (Prefinished Flashings) |  |  | X | [14 empty] | X
| 7.1 | Roof Specialties
| 7.10.01 | Roof Hatch - Product Data |  |  | X | [14 empty] | X
| 7.10.02 | Roof Hatch - Shop Drawings/Cut Sheets |  |  | X | X | [13 empty] | X
| 7.10.03 | Safety Pole/Ladder - Cut Sheets |  |  | X | X | [13 empty] | X
| 7.11 | Roof Anchors
| 7.11.01 | Roof Anchor - Product Data |  | X | X | X | X |  | X |  | X | [8 empty] | X
| 7.11.02 | Roof Anchor - Shop Drawings & Layout |  | X | X | X | X |  | X |  | X | [8 empty] | X
| 7.11.03 | Roof Anchor - Structural Calcs |  | X | X |  | X |  | X |  | X | [8 empty] | X
| 7.11.04 | Roof Anchor Testing & Certification |  | X | X | X | X |  | X |  | X | [8 empty] | X
| 7.11.05 | Horizontal Life Line Cable - Product Data |  | X | X | X | X |  | X |  | X | [8 empty] | X
| 7.11.06 | Portable Outrigger - Product Data |  | X | X | X | X |  | X |  | X | [8 empty] | X
| 7.12 | Fiber Cement Siding
| 7.12.01 | Fiber Cement Siding - Product Data (Trim, Lap, Panel, Fascia, Soffit) |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.12.02 | WRB |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.12.03 | Self Adhered Membranes |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.12.04 | Pressure Treated Battens/Furring Strips |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.12.05 | Fasteners and Anchors |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.12.06 | Joint Sealants |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.13 | Joint Sealants
| 7.13.01 | Joint Sealant - Product Data |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.13.02 | Air Barrier Sealant - Product Data |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.13.03 | Backer Rod - Product Data |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.13.04 | Color Selection - Samples (Prefinished Caulk Joints) |  |  | X |  |  |  |  | X | [9 empty] | X
| 7.14 | Firestopping
| 7.14.01 | Penetration Firestopping - Product Data |  | X | X | ? | [13 empty] | X
| 7.14.02 | 2HR fire caulk - Product Data |  | X | X | ? | [13 empty] | X
| 7.14.03 | Putty Pad - Product Data |  | X | X | ? | [13 empty] | X
| 7.14.04 | Fire Rated Collar/Boots (PT Deck Penetrations) |  | X | X | ? | [13 empty] | X
| 7.14.05 | Monokote (Spray Applied Fireproofing) - Product Data |  | X | X | ? | [13 empty] | X
| 7.14.06 | Project Specific - UL Listed Firestopping Assembly Book |  | X | X | ? | [13 empty] | X
Div 08 |  | Openings/Doors & Windows
| 8.1 | Doors & Hardware
| 8.1.01 | HM and Wood Door RO Schedule |  |  | X | X | [13 empty] | X
| 8.1.02 | Common Area Doors and Frame Product Data |  |  | X | [14 empty] | X
| 8.1.03 | Unit Doors and Frame Product Data |  |  | X | [14 empty] | X
| 8.1.04 | Door Hardware Schedule & Product Data |  |  | X | X | X | [9 empty] | X |  |  | X
| 8.1.05 | Electronic Door Hardware Product Data & Wiring Diagrams |  |  | X | X | X | [6 empty] | X | [5 empty] | X
| 8.1.06 | Gate Hardware Schedule & Product Data |  |  | X | X | X | [12 empty] | X
| 8.1.07 | Electronic Door Hardware |  |  | X | X | X | [6 empty] | X | [5 empty] | X
| 8.1.08 | Door Accessories (sweeps, soundseals, weatherstripping, etc.) |  |  | X | X | X | [10 empty] | X |  | X
| 8.1.09 | Common Area Keying Schedule |  |  | X | X | X | [12 empty] | X
| 8.2 | Aluminum Storefront
| 8.2.01 | Aluminum Storefront Shop Drawings |  |  | X | X | [13 empty] | X
| 8.2.02 | Storefront Frames & Glazing Product Data and Testing Data |  |  | X | [14 empty] | X
| 8.2.03 | Storefront Door Hardware Schedule |  |  | X | X | X | [12 empty] | X
| 8.2.04 | Storefront Frame Finish Selections (Brochure & Physical Samples) |  |  | X | [14 empty] | X
| 8.3 | Curtian Wall
| 8.3.01 | Curtain Wall Shop Drawings |  | X | X | X | [13 empty] | X
| 8.3.02 | Curtain Wall Product Data |  | X | X | [14 empty] | X
| 8.3.03 | Curtain Wall Finish Selections |  |  | X | [14 empty] | X
| 8.4 | Automatic Entrances
| 8.4.01 | Auto Entry Door Shop Drawings |  |  | X | X | [7 empty] | X | [5 empty] | X
| 8.4.02 | Auto Entry Frames and Glazing Product Data and Testing Data |  |  | X | [14 empty] | X
| 8.4.03 | Auto Entry Hardware Schedule |  |  | X | X | X | [12 empty] | X
| 8.4.04 | Auto Entry Door Wiring Diagram |  |  | X | X | [7 empty] | X | [5 empty] | X
| 8.4.05 | Auto Entry Door Frame Finish Selections (Brochure & Physical Samples) |  |  | X | [14 empty] | X
| 8.5 | Vinyl Windows & Doors
| 8.5.01 | Vinyl Windows & Doors Shop Drawings |  |  | X | X | [11 empty] | X |  | X
| 8.5.02 | Vinyl Windows & Door Product Data |  |  | X | [12 empty] | X |  | X
| 8.5.03 | Vinyl Windows & Door Testing Data |  |  | X | [12 empty] | X |  | X
| 8.5.04 | Manufacturer's Installation Guide & Requirements |  |  | X | X |  |  |  | X | [9 empty] | X
| 8.5.05 | Window Install Waterproofing Product Data |  |  | X |  |  |  |  | X | [9 empty] | X
| 8.5.06 | Window Water Test |  |  | X | X | X |  |  | X | [9 empty] | X
| 8.6 | OH & Rolling Coil Doors
| 8.6.01 | OH & Rolling Coil Door Shop Drawings |  |  | X | X |  |  | X |  |  |  |  | X | [5 empty] | X
| 8.6.02 | OH & Rolling Coil Door Product Data |  |  | X | [14 empty] | X
| 8.6.03 | OH & Rolling Coil Door Finish Selections |  |  | X | [14 empty] | X
| 8.6.04 | OH & Rolling Coil Door Wiring Diagram |  |  | X | X | X | [6 empty] | X | [5 empty] | X
| 8.7 | Operable Partitions
| 8.7.01 | Operable Partition Shop Drawings |  |  | X | X |  |  | X | [7 empty] | X | X |  | X
| 8.7.02 | Operable Partition Product Data |  |  | X | [11 empty] | X | X |  | X
| 8.7.03 | Operable Partition Finish Selections |  |  | X | [11 empty] | X |  |  | X
| 8.8 | Mirrors
| 8.8.01 | Unit Mirror Shop Drawings |  |  | X | X | [10 empty] | X |  |  | X
| 8.8.02 | Common Area Mirror Shop Drawings |  |  | X | X | [10 empty] | X |  |  | X
| 8.8.03 | Mirror Product Data |  |  | X | [11 empty] | X |  |  | X
Div 09 |  | Finishes
| 9.1 | Drywall & Light Gauge Framing
| 9.1.01 | Interior GWB Product Data |  |  | X | [14 empty] | X
| 9.1.02 | Exterior Densglass Product Data |  |  | X | [14 empty] | X
| 9.1.03 | Light Gauge Framing Product Data |  |  | X | [14 empty] | X
| 9.1.04 | 2HR Fire Wall Assembly H-Stud, Clips & CoreBoard Product Data |  |  | X | [14 empty] | X
| 9.1.05 | Shaft Wall Assembly H-Stud & Coreboard Product Data |  |  | X | [14 empty] | X
| 9.1.06 | Reslient Channel (RC Deluxe) & Hat Channel Product Data |  |  | X | [12 empty] | X |  | X
| 9.1.07 | RSIC Clips Product Data |  |  | X | [12 empty] | X |  | X
| 9.1.08 | Fasteners, Sealants & Accessory Product Data |  |  | X | [12 empty] | X |  | X
| 9.2 | ACT
| 9.2.01 | ACT Grid Product Data |  |  | X | [11 empty] | X | X |  | X
| 9.2.02 | ACT Tiles Product Data |  |  | X | [11 empty] | X | X |  | X
| 9.2.03 | ACT Tile Finish Selections |  |  | X | [11 empty] | X |  |  | X
| 9.3 | FRP & PLAM
| 9.3.01 | FRP Product Data |  |  | X | [11 empty] | X |  |  | X
| 9.3.02 | PLAM Product Data |  |  | X | [11 empty] | X |  |  | X
| 9.3.03 | Finish Selections |  |  | X | [11 empty] | X |  |  | X
| 9.4 | Acoustical Wall Treatment
| 9.4.01 | Acoustical Wall Covering Product Data |  |  | X | [11 empty] | X | X |  | X
| 9.4.02 | Acoustical Wall Covering Finish Selections |  |  | X | [11 empty] | X | X |  | X
| 9.5 | Stucco
| 9.5.01 | WRB & SAM Waterproofing Product Data |  |  | X |  |  |  |  | X | [9 empty] | X
| 9.5.02 | Rainscreen/Drain Mat Product Data |  |  | X |  |  |  |  | X | [9 empty] | X
| 9.5.03 | Exterior Rigid Insulation Product Data (if applicable) |  |  | X |  |  |  |  | X | [9 empty] | X
| 9.5.04 | Z-Girt Product Data (if applicable) |  |  | X |  |  |  |  | X | [9 empty] | X
| 9.5.05 | Stucco Plaster Product Data |  |  | X |  |  |  |  | X | [9 empty] | X
| 9.5.06 | Stucco Finish Coat Product Data |  |  | X |  |  |  |  | X | [9 empty] | X
| 9.5.07 | Stucco Finish Texture Sample |  |  | X | X |  |  |  | X | [9 empty] | X
| 9.5.08 | Stucco Accessories (lath, casings, j-molds, control joints, weep screed, etc..) |  |  | X | X |  |  |  | X | [9 empty] | X
| 9.5.09 | Control Joint Layout/Shop Drawings |  |  | X | X |  |  |  | X | [9 empty] | X
| 9.5.10 | Stucco Fasteners Product Data |  |  | X |  |  |  |  | X | [9 empty] | X
| 9.5.11 | Stucco Foam Trim Product Data & Shop Drawings |  |  | X |  |  |  |  | X | [9 empty] | X
| 9.5.12 | Exterior Joint Sealants Product Data |  |  | X |  |  |  |  | X | [9 empty] | X
| 9.6 | Flooring
| 9.6.01 | Resilient Flooring Product Data |  |  | X | [11 empty] | X |  |  | X
| 9.6.02 | Ceramic & Quarry Tile Flooring Product Data |  |  | X | [11 empty] | X |  |  | X
| 9.6.03 | Carpet Product Data |  |  | X | [11 empty] | X |  |  | X
| 9.6.04 | Sheet Vinyl Seam Diagram |  |  | X | X | X | [9 empty] | X |  |  | X
| 9.6.05 | Carpet Seam Diagram |  |  | X | X | X | [9 empty] | X |  |  | X
| 9.6.06 | Tile Flooring Layout Diagram |  |  | X | X | X | [9 empty] | X |  |  | X
| 9.6.07 | Anti-Fracture & Waterproofing Membrane Product Data |  |  | X |  | X | [9 empty] | X |  |  | X
| 9.6.08 | Floor Leveling Compound Product Data |  |  | X | [14 empty] | X
| 9.6.09 | Flooring Accessories (schluter, transition strips, primer, sealers, etc..) |  |  | X | [11 empty] | X |  |  | X
| 9.6.10 | Tile Grout Finish Selection |  |  | X |  | X | [9 empty] | X |  |  | X
| 9.6.11 | Moisture Testing Reports |  |  | X | X | X | [12 empty] | X
| 9.7 | Paint, Coatings & Wall Coverings
| 9.7.01 | Interior Paint Product Data |  |  | X | [11 empty] | X |  |  | X
| 9.7.02 | Exterior Paint Product Data |  |  | X | [11 empty] | X |  |  | X
| 9.7.03 | Electrostatic Paint Product Data |  |  | X | [11 empty] | X |  |  | X
| 9.7.04 | Paint Draw-Down Samples |  |  | X | [11 empty] | X |  |  | X
| 9.7.05 | Wall Covering Product Data |  |  | X | [11 empty] | X |  |  | X
| 9.7.06 | Wall Covering Samples |  |  | X | [11 empty] | X |  |  | X
| 9.7.07 | Sealer Product Data |  |  | X | [11 empty] | X |  |  | X
| 9.7.08 | Anti-Graffiti Coating Product Data |  |  | X |  | X |  |  | X | [9 empty] | X
Div 10 |  | Specialties
| 10.1 | Interior Signage
| 10.1.01 | Interior Signage Programming |  | X | X | X | X | [9 empty] | X |  |  | X
| 10.1.02 | Interior Signage Shop Drawings |  | X | X | X | X | [9 empty] | X |  |  | X
| 10.1.03 | Fire Dept Red & White Signage |  | X | X | X | X | [12 empty] | X
| 10.1.04 | ADA Signage |  | X | X | X | X | [12 empty] | X
| 10.1.05 | Emergency Evac Maps |  | X | X | X | X | [12 empty] | X
| 10.2 | Exterior Signage
| 10.2.01 | Exterior Signage Programming |  | X | X | X | X | [6 empty] | X | [5 empty] | X
| 10.2.02 | Exterior Signage Shop Drawings |  | X | X | X | X | [6 empty] | X | [5 empty] | X
| 10.2.03 | Pool Signage Shop Drawings |  | X | X | X | X | [12 empty] | X
| 10.2.04 | Entry Monument Signage Shop Drawings |  | X | X | X | X |  | X |  |  |  |  | X | [5 empty] | X
| 10.2.05 | Parking Lot Directional Signage Shop Drawings |  | X | X | X | X | [12 empty] | X
| 10.3 | Bath Accessories
| 10.3.01 | Unit Bath Accessories Product Data |  |  | X | [11 empty] | X |  |  | X
| 10.3.02 | Common Area Bath Accessories Product Data |  |  | X | [11 empty] | X |  |  | X
| 10.3.03 | Finish Selections |  |  | X | [11 empty] | X |  |  | X
| 10.4 | Postal Specialties
| 10.4.01 | Mailbox Shop Drawings |  | X | X | X | X | [12 empty] | X
| 10.4.02 | Mailbox Product Data |  | X | X |  | X | [12 empty] | X
| 10.4.03 | Finish & Engraving Selection |  | X | X |  | X | [9 empty] | X |  |  | X
| 10.4.04 | Post Office & Owner/Operator Approved Address Labeling |  | X | X | X | X | [12 empty] | X
| 10.5 | Fire Dept Knox Boxes
| 10.5.01 | Know Box Product Data |  | X | X | X | [13 empty] | X
| 10.5.02 | Know Box Exterior Wall RO & Mounting Requirements |  | X | X | X | [13 empty] | X
| 10.6 | Flagpoles
| 10.6.01 | Flagpole Shop Drawings |  |  | X | X | [12 empty] | X | X
| 10.6.02 | Flagpole Product Data & Finish Selection |  |  | X | [13 empty] | X | X
| 10.6.03 | Flagpole Footing Design |  |  | X | X |  |  | X | [10 empty] | X
| 10.7 | Fire Extinguishers & Cabinets
| 10.7.01 | Fire Extinguisher Cabinet Product Data |  |  | X | X | [13 empty] | X
| 10.7.02 | Fire Extinguisher Product Data |  |  | X | [14 empty] | X
Div 11 |  | Equipment
| 11.1 | Residential Appliances
| 11.1.01 | Unit Kitchen Appliance Product Data |  |  | X | X | X |  |  |  |  | X |  | X |  |  | X |  |  | X
| 11.1.02 | Unit Appliance Cooktop cutout template |  |  | X | X | [7 empty] | X | [5 empty] | X
| 11.1.03 | Unit Laundry Washer & Dryer Product Data |  |  | X | X | X |  |  |  |  | X |  | X |  |  | X |  |  | X
| 11.2 | Commercial Laundry Equipment
| 11.2.01 | Commercial Laundry Equipment Product Data |  |  | X |  | X |  |  |  |  | X |  | X | [5 empty] | X
| 11.2.02 | Commercial Laundry Equipment Shop Drawings |  |  | X | X | X |  |  |  |  | X |  | X | [5 empty] | X
| 11.3 | Commercial Kitchen Equipment
| 11.3.01 | Commercial Kitchen Equipment Product Data |  |  | X |  | X |  |  |  |  | X |  | X |  | X |  |  |  | X
| 11.3.02 | Commercial Kitchen Hood Shop Drawings |  |  | X | X | X |  |  |  |  | X |  | X |  | X |  |  |  | X
| 11.3.03 | Commercial Kitchen Walk-In Refer/Freezer Shop Drawings |  |  | X | X | X | [6 empty] | X |  | X |  |  |  | X
| 11.3.04 | Remote Condenser Shop Drawings |  |  | X | X | X |  | X |  |  |  |  | X |  | X |  |  |  | X
| 11.3.05 | Ansul System Shop Drawings |  |  | X | X | [6 empty] | X |  |  | X |  |  |  | X
| 11.3.06 | Commercial Kitchen Stainless Steel Countertop Shop Drawings |  |  | X | X | [9 empty] | X | X |  |  | X
| 11.4 | Solid Waste Equipment
| 11.4.01 | Trash Compactor Shop Drawings |  |  | X | X | X | [6 empty] | X | [5 empty] | X
| 11.4.02 | Trash Bin Product Data |  |  | X |  | X | [12 empty] | X
| 11.4.03 | Cart Caddy Product Data |  |  | X |  | X | [12 empty] | X
| 11.5 | Fitness Equipment
| 11.5.01 | Fitness Equipment Layout |  |  | X | X | X | [6 empty] | X |  |  | X |  |  | X
| 11.5.02 | Fitness Equipment Specs - Power & Internet Requirements |  |  | X | X | X | [6 empty] | X |  |  | X |  |  | X
| 11.6 | Audio/Visual Equipment
| 11.6.01 | Theater A/V Design |  |  | X | X | X | [6 empty] | X |  |  | X |  |  | X
| 11.6.02 | Theater A/V Equipment Specs |  |  | X |  | X | [6 empty] | X |  |  | X |  |  | X
| 11.6.03 | Common Area/Corridor Sound System Design |  |  | X | X | X | [6 empty] | X |  |  | X |  |  | X
| 11.6.04 | Sound System Equipment Specs |  |  | X |  | X | [6 empty] | X |  |  | X |  |  | X
Div 12 |  | Furnishings
| 12.1 | Residential Casework - Cabinets
| 12.1.01 | Unit Cabinet Shop Drawings |  |  | X | X | [10 empty] | X |  |  | X
| 12.1.02 | Memory Care Wardrobe Shop Drawings |  |  | X | X | [10 empty] | X |  |  | X
| 12.1.03 | Cabinet Product Data |  |  | X | [11 empty] | X |  |  | X
| 12.1.04 | Cabinet Finish Selections |  |  | X | [11 empty] | X |  |  | X
| 12.1.05 | Cabinet Pulls Finish Selection |  |  | X | [11 empty] | X |  |  | X
| 12.2 | Unit Countertops
| 12.2.01 | Unit Countertop Shop Drawings |  |  | X | X | [10 empty] | X |  |  | X
| 12.2.02 | Unit Countertop Product Data |  |  | X | [11 empty] | X |  |  | X
| 12.2.03 | Unit Countertop Finish Selection & Samples |  |  | X | [11 empty] | X |  |  | X
| 12.2.04 | Sink/Cooktop/Plumbing Fixture Cut-Out Templates |  |  | X | X | [13 empty] | X
| 12.3 | Common Area Countertops
| 12.3.01 | Common Area Countertop Shop Drawings |  |  | X | X | [10 empty] | X |  |  | X
| 12.3.02 | Common Area Countertop Product Data |  |  | X | [11 empty] | X |  |  | X
| 12.3.03 | Common Area Countertop Finish Selection & Samples |  |  | X | [11 empty] | X |  |  | X
| 12.4 | Window Coverings
| 12.4.01 | Unit Window Blinds Product Data |  |  | X |  | X | [9 empty] | X |  |  | X
| 12.4.02 | Unit Window Blinds Finish Selection |  |  | X |  | X | [9 empty] | X |  |  | X
| 12.4.03 | Unit Patio Door Blinds Product Data |  |  | X |  | X | [9 empty] | X |  |  | X
| 12.5 | Site Furnishings
| 12.5.01 | Bike Rack Product Data & Finish Selections |  |  | X | [13 empty] | X | X
| 12.5.02 | Planter Box & Pottery Product Data & Finish Selections |  |  | X | [13 empty] | X | X
| 12.5.03 | BBQ Specs & Install Guide |  |  | X | X | X | [6 empty] | X |  |  |  |  | X | X
| 12.5.04 | Fire Pit Shop Drawings & Product Data |  |  | X | X | [7 empty] | X |  |  |  |  | X | X
| 12.5.05 | Site Benches Product Data |  |  | X | [13 empty] | X | X
| 12.5.06 | **Project Specific Furnishings** |  |  | X | X | [12 empty] | X | X
Div 13 |  | Special Construction
| 13.1 | Swimming Pool
| 13.1.01 | Swimming Pool Permitted Design/Drawings |  | X | X | X | X | [6 empty] | X | [5 empty] | X
| 13.1.02 | Pool Equipment Spec's |  | X | X | X | [7 empty] | X | [5 empty] | X
| 13.1.03 | Pool Coping Mix Design & Shop Drawings |  | X | X | X | [13 empty] | X
| 13.1.04 | Pool Code Signage |  | X | X | X | [13 empty] | X
| 13.2 | Water Features/Fountains
| 13.2.01 | Water Feature Product Data |  |  | X |  | X | [6 empty] | X |  |  |  |  | X | X
| 13.2.02 | Water Feature Shop Drawings |  |  | X | X | X | [6 empty] | X |  |  |  |  | X | X
| 13.3 | Solar Systems
| 13.3.01 | **Project Specific Requirment** |  | X | X |  | X | [6 empty] | X | [5 empty] | X
Div 14 |  | Conveying Systems
| 14.1 | Elevators
| 14.1.01 | Elevator Pit Drawings |  |  | X | X |  |  | X | [10 empty] | X
| 14.1.02 | Elevator Shop Drawings |  |  | X | X | X |  | X |  |  |  |  | X | [5 empty] | X
| 14.1.03 | Elevator Cab Finish Selections |  |  | X |  | X | [9 empty] | X |  |  | X
| 14.2 | Dumbwaiters
| 14.2.01 | Dumbwaiter Shop Drawings |  |  | X | X | X |  | X |  |  |  |  | X | [5 empty] | X
| 14.2.02 | Dumbwaiter Product Data & Finish Selections |  |  | X |  | X | [9 empty] | X |  |  | X
| 14.3 | Trash Chutes
| 14.3.01 | Trash Chute Shop Drawings |  |  | X | X | X |  | X |  |  |  |  | X | [5 empty] | X
| 14.3.02 | Trash Chute Product Data |  |  | X | X | X | [12 empty] | X
| 14.3.03 | Trash Chute Acoustical Treatments |  |  | X | X | [11 empty] | X |  | X
Div 21 |  | Fire Suppression
| 21.1 | Fire Sprinkler
| 21.1.01 | Fire Sprinkler Permitted Design/Drawings |  | X | X | X | X | [5 empty] | X | X | [5 empty] | X
| 21.1.02 | Fire Sprinkler Equipment Specs (Fire Pump if required) |  | X | X | X | [7 empty] | X | [5 empty] | X
| 21.1.03 | Fire Sprinkler Product Data |  |  | X | [14 empty] | X
| 21.1.04 | Fasteners & Adhesives Product Data |  |  | X | [14 empty] | X
Div 22 |  | Plumbing
| 22.1 | Plumbing Materials & Equipment
| 22.1.01 | Plumbing Equipment Cut Sheets (Booster Pump, Re-Circ, Boilers/Water Heater, Storage Tanks, Sump Pumps, etc..) |  |  | X | X | [6 empty] | X | X | [5 empty] | X
| 22.1.02 | Sewage Ejector Pump Shop Drawings |  |  | X | X | [6 empty] | X | X | [5 empty] | X
| 22.1.03 | Grease Interceptor Shop Drawings |  |  | X | X |  | X |  |  |  |  | X | [6 empty] | X
| 22.1.04 | Water Pipe/Material Product Data (Copper, CPVC, PEX, Fittings, etc.) |  |  | X | [7 empty] | X |  |  |  |  | X |  | X
| 22.1.05 | Waste/Vent/Drain Material Product Data |  |  | X | [7 empty] | X |  |  |  |  | X |  | X
| 22.1.06 | Gas Piping Product Data |  |  | X | [7 empty] | X | [6 empty] | X
| 22.1.07 | Roof Drains & Overflow Drain Product Data |  |  | X | [7 empty] | X | [6 empty] | X
| 22.1.08 | Hose-Bib Product Data |  |  | X |  | X | [5 empty] | X | [6 empty] | X
| 22.1.09 | Adhesives, Primers and Accessories Product Data |  |  | X | [7 empty] | X | [6 empty] | X
| 22.1.10 | Acoustical Treatments |  |  | X | X | [6 empty] | X |  |  |  |  | X |  | X
| 22.2 | Plumbing Fixtures
| 22.2.01 | Unit Plumbing Fixture Product Data |  |  | X |  | X | [5 empty] | X |  |  |  | X |  |  | X
| 22.2.02 | Common Area Plumbing Fixture Product Data |  |  | X | [7 empty] | X |  |  |  | X |  |  | X
| 22.2.03 | Plumbing Fixture Finish Selections |  |  | X |  | X | [5 empty] | X |  |  |  | X |  |  | X
| 22.3 | Tub/Showers
| 22.3.01 | Tub/Shower Shop Drawings |  |  | X | X | X | [5 empty] | X | [6 empty] | X
| 22.3.02 | Tub/Shower Installation Instructions |  |  | X | X | [6 empty] | X | [6 empty] | X
Div 23 |  | HVAC
| 23.1 | HVAC Equipment & Materials
| 23.1.01 | HVAC Equipment Shop Drawings w/RO Schedule/Layout (Floors/Walls & Roof) |  |  | X | X |  |  | X |  |  | X |  | X | [5 empty] | X
| 23.1.02 | MAU & KEF Equipment Cut Sheets/Shop Drawings |  |  | X | X | [5 empty] | X |  | X |  | X |  | X |  | X
| 23.1.03 | VRF Equipment Cut Sheets/Shop Drawings |  |  | X | X | [5 empty] | X |  | X |  |  |  | X |  | X
| 23.1.04 | Refrigerant/Line Set Shop Drawings & Product Data |  |  | X | X | [5 empty] | X | [7 empty] | X
| 23.1.05 | VTAC Equipment Cut Sheets/Shop Drawings |  |  | X | X | [5 empty] | X |  | X |  |  |  | X |  | X
| 23.1.06 | Acoustical Treatments (Spring Isolators, Curbs, Neoprene Pads) |  |  | X | X | [5 empty] | X | [5 empty] | X |  | X
| 23.1.07 | Grease Duct Product Data |  |  | X | X | [5 empty] | X | [7 empty] | X
| 23.1.08 | Grease Duct Access Doors |  |  | X | X | [5 empty] | X | [7 empty] | X
| 23.1.09 | Exhaust Fan Cut Sheets |  |  | X | [6 empty] | X |  | X |  |  |  | X |  | X
| 23.1.10 | Ductless Split System Cut Sheets |  |  | X | [6 empty] | X |  | X | [5 empty] | X
| 23.1.11 | Fresh Air Fan Cut Sheets |  |  | X | [6 empty] | X | [5 empty] | X |  | X
| 23.1.12 | Fire Smoke Dampers Product Data |  |  | X | [6 empty] | X |  | X | [5 empty] | X
| 23.1.13 | Fire Dampers Product Data |  |  | X | [6 empty] | X |  | X | [5 empty] | X
| 23.1.14 | Diffusers, Registers, Louvers & Grilles Product Data |  |  | X | [6 empty] | X | [7 empty] | X
| 23.1.15 | Sheet Metal Duct Product Data |  |  | X | [6 empty] | X | [7 empty] | X
| 23.1.16 | Duct Wrap & Insulation Product Data |  |  | X | [6 empty] | X | [5 empty] | X |  | X
| 23.1.17 | Hangers & Pipe Support Product Data |  |  | X | [6 empty] | X | [7 empty] | X
| 23.1.18 | Unit Venting & Exterior Shrouds Product Data & Shop Drawings |  |  | X | X | [5 empty] | X | [7 empty] | X
| 23.1.19 | Dryer Booster Fans & Lint Trap Product Data |  |  | X | X | [5 empty] | X |  | X | [5 empty] | X
| 23.1.20 | Dryer Vent Boxes |  |  | X | X | [5 empty] | X | [7 empty] | X
| 23.1.21 | Thermostats |  |  | X | [6 empty] | X | [7 empty] | X
| 23.1.22 | TAB Report |  | X | X | X | [5 empty] | X | [7 empty] | X
Div 26 |  | Electrical
| 26.1 | Electrical Materials & Equipment
| 26.1.01 | Switchgear, Switchboards & Panelboard Shop Drawings |  | X | X | X | [7 empty] | X | [5 empty] | X
| 26.1.02 | Transformer Equipment Cut Sheets |  |  | X | X | [7 empty] | X | [5 empty] | X
| 26.1.03 | Disconnect & Switches Cut Sheets |  |  | X | X | [7 empty] | X | [5 empty] | X
| 26.1.04 | Sub-Panel Cut Sheets |  |  | X | [8 empty] | X | [5 empty] | X
| 26.1.05 | Grounding & Bonding Material Package |  |  | X | [8 empty] | X | [5 empty] | X
| 26.1.06 | Hangers & Supports Product Data |  |  | X | [8 empty] | X | [5 empty] | X
| 26.1.07 | Raceways and Boxes Product Data |  |  | X | [8 empty] | X | [5 empty] | X
| 26.1.08 | Wiring Devices Product Data |  |  | X | [8 empty] | X | [5 empty] | X
| 26.1.09 | Emergency Inverter Shop Drawings/Cut Sheets |  |  | X | X | [7 empty] | X | [5 empty] | X
| 26.1.10 | Lock-Out Tag-Out Package |  | X | X | X | [7 empty] | X | [5 empty] | X
| 26.2 | Lighting Controls
| 26.2.01 | Inverter Cut Sheets |  |  | X | [8 empty] | X | X |  |  |  |  | X
| 26.2.02 | Occupancy Sensors, Dimmers, Photocell and Timer Product Data |  |  | X | [8 empty] | X | X |  |  |  |  | X
| 26.3 | Light Fixtures
| 26.3.01 | Light Fixture Submittal Package |  |  | X | X | X | [6 empty] | X | X |  | X |  |  | X
| 26.3.02 | - Unit Light Fixtures |  |  | X | X | X | [6 empty] | X | X |  | X |  |  | X
| 26.3.03 | - Common Area/Corridor Light Fixtures |  |  | X | X | X | [6 empty] | X | X |  | X |  |  | X
| 26.3.04 | - Service Area/BOH Light Fixtures |  |  | X | X | X | [6 empty] | X | X |  |  |  |  | X
| 26.3.05 | - Decorative/Specialty Light Fixtures |  |  | X | X | X | [6 empty] | X | X |  | X |  |  | X
| 26.3.06 | - Exterior Building Lighting Fixtures |  |  | X | X | X | [6 empty] | X | X |  |  |  |  | X
| 26.3.07 | - Site Light Fixtures |  |  | X | X | X | [6 empty] | X | X |  |  |  | X | X
| 26.4 | Electric Vehicle Charging Stations
| 26.4.01 | EV Charger Product Data |  |  | X | X | [7 empty] | X | [5 empty] | X
Div 27 |  | Communications
| 27.1 | Low Voltage Materials & Equipment
| 27.1.01 | Low Voltage Equipment Product Data (Cabling, Racks, Patch Panels, Terminations, etc.) |  |  | X |  | X | [6 empty] | X | [5 empty] | X
| 27.1.02 | Unit Smart Panel/Media Can Cut Sheets |  |  | X |  | X | [6 empty] | X | [5 empty] | X
| 27.2 | WIFI AP System
| 27.2.01 | WIFI AP Design/Layout |  |  | X | X | X | [6 empty] | X | [5 empty] | X
| 27.2.02 | WIFI AP Equipment Product Data |  |  | X |  | X | [6 empty] | X | [5 empty] | X
| 27.3 | Nurse Call System
| 27.3.01 | Nurse Call & Wander Management/Access Control Design |  | X | X | X | X | [6 empty] | X | [5 empty] | X
| 27.3.02 | Nurse Call Equipment Product Data |  |  | X | X | X | [6 empty] | X | [5 empty] | X
| 27.3.03 | Access Control Equipment (Door Hardware, Repeaters, WAP's, Power Supplies, etc.) |  |  | X | X | X | [6 empty] | X | [5 empty] | X
| 27.4 | Access Control
| 27.4.01 | Nurse Call & Wander Management/Access Control Design |  |  | X | X | X | [6 empty] | X | [5 empty] | X
| 27.4.02 | Wanderguard Blue Equipment Cut Sheets |  |  | X | X | X | [6 empty] | X | [5 empty] | X
| 27.4.03 | Door Hardware Cut Sheets & Wiring Diagrams |  |  | X | X | X | [6 empty] | X | [5 empty] | X
| 27.4.04 | Keypads Cut Sheet & Wiring Diagrams |  |  | X | X | X | [6 empty] | X | [5 empty] | X
| 27.4.05 | Intercom/AirPhone Cut Sheets |  |  | X | X | X | [6 empty] | X | [5 empty] | X
| 27.5 | Two Way Communication
| 27.5.01 | Two Way Communication Permitted Design/Drawings |  | X | X | X | [7 empty] | X | [5 empty] | X
| 27.5.02 | Two Way Communication Equipment Cut Sheets |  | X | X | X | [7 empty] | X | [5 empty] | X
| 27.6 | ERRCS
| 27.6.01 | ERRCS Permitted Design/Drawings |  | X | X | X | [7 empty] | X | [5 empty] | X
| 27.6.02 | ERRCS Equipment Cut Sheets |  | X | X | X | [7 empty] | X | [5 empty] | X
| 27.6.03 | ERRCS Site Survey |  | X | X | X | [13 empty] | X
| 27.6.04 | ERRCS Testing, Commissioning & Inspection Reports |  | X | X | X | [13 empty] | X
| 27.7 | Cell Booster System
| 27.7.01 | Cell Booster Site Survey |  |  | X | X | X | [12 empty] | X
| 27.7.02 | Cell Booster System Design |  |  | X | X | X | [6 empty] | X | [5 empty] | X
| 27.7.03 | Cell Booster System Equipment & Material Cut Sheets |  |  | X | X | X | [6 empty] | X | [5 empty] | X
| 27.7.04 | Cell Booster System Testing & Commissioning Reports |  |  | X | X | X | [12 empty] | X
Div 28 |  | Electronic Safety & Security
| 28.1 | Fire Alarm
| 28.1.01 | Fire Alarm Permitted Design/Drawings |  | X | X | X | X |  |  |  |  | X |  | X | [5 empty] | X
| 28.1.02 | Fire Alarm Equipment Cut Sheets (FACP, Annunicator) |  | X | X | X | X | [6 empty] | X | [5 empty] | X
| 28.1.03 | Fire Alarm Material Product Data |  | X | X |  | X | [12 empty] | X
| 28.2 | CCTV
| 28.2.01 | CCTV Design/Shop Drawing Layout |  |  | X | X | X | [6 empty] | X | [5 empty] | X
| 28.2.02 | CCTV Material Product Data (Cabling Req, Camera Spec's) |  |  | X |  | X | [12 empty] | X
Div 31 |  | Earthwork
| 31.1 | Mass Ex & Fine Grading
| 31.1.01 | Import Soil - Engineered Fill Product Data & Sample |  |  | X | X | [13 empty] | X
| 31.2 | Shoring Wall & Tie Backs
| 31.2.01 | Shoring System Shop Drawings |  | X | X | X |  |  | X | [10 empty] | X
| 31.2.02 | Shoring System Product Data |  |  | X |  |  |  | X | [10 empty] | X
| 31.2.03 | Concrete Mix Design |  |  | X | X |  |  | X | [10 empty] | X
| 31.3 | Erosion Control
| 31.3.01 | BMP Product Data |  |  | X | X | [13 empty] | X
| 31.4 | Termite Control
| 31.4.01 | Termite Control Product Data |  |  | X | [14 empty] | X
Div 32 |  | Exterior Improvements
| 32.1 | Asphalt Paving
| 32.1.01 | Asphalt Public ROW Product Data |  | X | X |  |  | X | [11 empty] | X
| 32.1.02 | Base Agg Public ROW Product Data |  | X | X |  |  | X | [11 empty] | X
| 32.1.03 | Asphalt Onsite Product Data |  |  | X |  |  | X | [11 empty] | X
| 32.1.04 | Base Agg Onsite Product Data |  |  | X |  |  | X | [11 empty] | X
| 32.1.05 | Striping & Wheelstop Product Data & Layout |  |  | X | X |  | X | [11 empty] | X
| 32.2 | Site Concrete (Curb, Gutter, Sidewalk)
| 32.2.01 | Concrete Mix Designs |  |  | X | X |  | X | [11 empty] | X
| 32.2.02 | Rebar/Reinforcement Product Data |  |  | X |  |  | X | [11 empty] | X
| 32.2.03 | Topcast Finish Product Data |  |  | X | [13 empty] | X | X
| 32.2.04 | Color Finish Selection |  |  | X | [13 empty] | X | X
| 32.3 | Pavers
| 32.3.01 | Paver Product Data |  |  | X | [13 empty] | X | X
| 32.3.02 | Paver Finish Selection |  |  | X | X | [12 empty] | X | X
| 32.3.03 | Pedestal Product Data |  |  | X | [13 empty] | X | X
| 32.4 | Fencing & Gates
| 32.4.01 | Fencing & Gates Shop Drawings |  |  | X | X | [12 empty] | X | X
| 32.4.02 | Fencing & Gates Product Data & Finish Selection |  |  | X | [13 empty] | X | X
| 32.5 | Greenscreen
| 32.5.01 | Greenscreen Shop Drawings |  |  | X | X | [12 empty] | X | X
| 32.5.02 | Greenscreen Product Data & Finish Selection |  |  | X | [13 empty] | X | X
| 32.6 | Landscape & Irrigation
| 32.6.01 | Irrigation Equipment Cut Sheets (Booster Pumps, Controls, etc.) |  |  | X | [8 empty] | X |  |  |  |  | X | X
| 32.6.02 | Irrigation Material Product Data |  |  | X | [13 empty] | X | X
| 32.6.03 | Landscape Planting Schedule & Product Data |  |  | X | [13 empty] | X | X
| 32.6.04 | Landscape Planting Samples/Photos |  |  | X | [13 empty] | X | X
| 32.6.05 | Landscape Material Product Data (root barrier, tree stakes, etc.) |  |  | X | [13 empty] | X | X
| 32.6.06 | Mulch/Topsoil Product Data |  |  | X | [13 empty] | X | X
| 32.6.07 | Green Tray Product Data |  |  | X | [13 empty] | X | X
| 32.6.08 | Decomposed Granite/Cobble/Ballast Product Data |  |  | X | [13 empty] | X | X
| 32.6.09 | Tree Well/Grate Shop Drawings & Product Data |  |  | X | X |  | X | [10 empty] | X | X
Div 33 |  | Utilities
| 33.1 | Underground Wet Utilities
| 33.1.01 | Structure/Vault/Manhole Shop Drawings |  | X | X | X |  | X | [11 empty] | X
| 33.1.02 | Piping Material Product Data |  | X | X |  |  | X | [11 empty] | X
| 33.1.03 | Concrete Mix Designs & Bedding/Backfill Product Data |  |  | X | X |  | X | [11 empty] | X
| 33.1.04 | Valves, Fittings, Joints Product Data |  | X | X |  |  | X | [11 empty] | X
| 33.2 | Dry Utilities
| 33.2.01 | Structures/Vaults/Slab Box/PME Shop Drawings |  | X | X | X | [7 empty] | X | [5 empty] | X
| 33.2.02 | Piping Material Product Data |  | X | X | [14 empty] | X
| 33.2.03 | Concrete Mix Designs |  |  | X | X | [13 empty] | X
Div 34 |  | Transportation
| 34.1 | Traffic Signals
| 34.1.01 | **Project Specific Requirements** |  |  | X | X
Div 70 |  | Tenant TI's & FFE

## Submittal Packages Template
Division | Submittal # | Section Title & Description | Long Lead Time - Comments | SRM Construction | Owner's Rep | Civil Engineer | Strutural Engineer | Mechanical Engineer | Plumbing Engineer | Electrical Engineer | Lighting Consultant | Interior Designer | Acoustical Consultant | Landscape Architect | Architect
Div 02 |  | Existing Conditions/Demolition
Div 03 |  | Concrete
Div 04 |  | Masonry
Div 05 |  | Metals
Div 06 |  | Rough Carpentry
Div 07 |  | Thermal & Moisture Protection
Div 08 |  | Openings/Doors & Windows
Div 09 |  | Finishes
Div 10 |  | Specialties
Div 11 |  | Equipment
Div 12 |  | Furnishings
Div 13 |  | Special Construction
Div 14 |  | Conveying Systems
Div 21 |  | Fire Suppression
Div 22 |  | Plumbing
Div 23 |  | HVAC
Div 26 |  | Electrical
Div 27 |  | Communications
Div 28 |  | Electronic Safety & Security
Div 31 |  | Earthwork
Div 32 |  | Exterior Improvements
Div 33 |  | Utilities
Div 34 |  | Transportation
Div 70 |  | Tenant TI's & FFE